## Slide 1: Software Project Management
Dr. Sumaira Nazir
Assistant Professor,
Department of software engineering
National University Of Modern Languages H-9 Islamabad
Project Cost Management

## Slide 2: Project Cost Management
National University Of Modern Languages H-9 Islamabad

## Slide 3: Project Cost Management
Includes the processes required to ensure that a project team completes a project within an approved budget.
Why Cost Management is Important?
      Projects fail primarily due to cost overruns
      IT projects often have hidden or intangible cost elements
      Ensures resources are used efficiently
      Allows management to track financial performance
There are four processes for project cost management
  Planning cost management
  Estimating costs
  Determining the budget
  Controlling costs

## Slide 4: Processes for project cost management
1. Planning cost management
  involves determining the policies, procedures, and documentation that will be used for
    Planning
    Executing
    and controlling project cost.
  The main output of this process is a cost management plan.

## Slide 5: Processes for project cost management
2. Estimating costs
Involves developing an approximation or estimate of the costs of the resources needed to complete a project.
The main outputs of the cost estimating process are
  activity cost estimates
  project documents updates.

## Slide 6: Processes for project cost management
3. Controlling costs involves
  Controlling changes to the project budget.
  The main outputs of the cost control process are
    work performance information
    cost forecasts
    change requests and project management plan updates,
    project documents updates.

## Slide 7: Basic Principles of Cost Management
Profits
  are revenues minus expenditures
Life cycle costing
  provides a big-picture view of the cost of a project throughout its life cycle

## Slide 8: Basic Principles of Cost Management
Direct costs
  can be directly related to creating the products and services of the project
Indirect costs
  are not directly related to the products or services of the project, but are indirectly related to performing work on the project. For example, indirect costs would include the cost of electricity, paper

## Slide 9: Basic Principles of Cost Management
Sunk cost
  is money that has been spent in the past
Learning curve theory
  states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced.

## Slide 10: Basic Principles of Cost Management
Learning curve theory
  Example,
    Suppose a project would potentially produce 1,000 handheld devices that could run the new software and access information via satellite.
    The cost of the first handheld unit would be much higher than the cost of the thousandth unit.
    Learning curve theory can help estimate costs on projects that involve the production of large quantities of items

## Slide 11: Basic Principles of Cost Management
Reserves
  amounts included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict.
    Contingency reserves
    Management reserves

## Slide 12: Basic Principles of Cost Management
Contingency reserves
  allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline.
  For example, if an organization knows it has a 20 percent rate of turnover for IT personnel, it should include contingency reserves to pay for recruiting and training costs of IT personnel.

## Slide 13: Basic Principles of Cost Management
Management reserves
  allow for future situations that are unpredictable (sometimes called unknown unknowns).
  For example, if a project manager gets sick for two weeks or an important supplier goes out of business, management reserve could be set aside to cover the resulting costs.

## Slide 14: Processes for project cost management
There are four processes for project cost management
  Planning cost management
  Estimating costs
  Determining the budget
  Controlling costs

## Slide 15: Processes for project cost management
Planning cost management
  involves determining the policies, procedures, and documentation that will be used
  for planning, executing, and controlling project cost.
  The main output of this process is a cost management plan.

## Slide 16: Planning Cost Management
Level of accuracy:
  Activity cost estimates normally have rounding guidelines, such as rounding to the nearest $100.
Units of measure:
  Each unit used in cost measurements, such as
    Labor cost-labor hours or days, should be defined.
    Hardware Cost-dollars or units purchased.
    Clear definitions prevent confusion between different departments, such as finance and operations.

## Slide 17: Planning Cost Management
Organizational procedures links:
  This connects cost management processes to organizational systems, like accounting or reporting, often referencing the Work Breakdown Structure (WBS).
Example:
  A marketing campaign project might assign a unique control account code (e.g., CA-1001) to the design phase. This code is used in the company’s accounting software to track expenses and ensure accurate reporting.

## Slide 18: Planning Cost Management
Control thresholds:
  These are the limits of acceptable variance in cost, beyond which corrective actions must be taken.
Example:
  For a manufacturing project, if the baseline cost is $50,000, a 10% threshold means any cost variation exceeding $5,000 (either over or under) triggers an analysis and potential adjustments.

## Slide 19: Planning Cost Management
  Rules of performance measurement: The cost management plan would define measurement rules, such as how often actual costs will be tracked and to what level of detail.
  Example
    In an IT project, the team might track actual costs every two weeks and compare them with planned costs using metrics like Cost Performance Index (CPI). If CPI falls below 0.9, it indicates a cost overrun requiring immediate action.

## Slide 20: Planning Cost Management
Reporting formats:
This section would describe the format and frequency of cost reports required for the project. Ensuring stakeholders receive consistent and timely information.
Example:
A construction project might require a weekly cost summary report showing expenses by phase (e.g., design, procurement, construction) in a tabular format with graphs for trends.

## Slide 21: Planning Cost Management
Process descriptions:
  The cost management plan would also describe how to perform all of the cost management processes
  Example
  For a renewable energy project, the cost management plan might outline how to:
    Collect cost estimates from vendors.
    Approve budgets through management.
    Track expenses weekly.
    Handle budget revisions if costs exceed the threshold.

## Slide 22: Processes for project cost management
Estimating costs involves
  developing an approximation or estimate of the costs of the resources needed to complete a project.
  The main outputs of the cost estimating process are
  activity cost estimates, and project documents updates.

## Slide 23: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints.
After developing a good resource requirements list, project managers and their project teams must develop several estimates of the costs for these resources.

## Slide 24: Types of Cost Estimates
A rough order of magnitude (ROM)
A budgetary estimate
A definitive estimate

## Slide 25: Types of Cost Estimates
A rough order of magnitude (ROM)
  estimate provides an estimate of what a project will cost.
  referred to as a guesstimate, a broad gauge.
  It is done very early in a project or even before a project is officially started.
  Purpose:
    Project managers and top management use this estimate to help make project selection decisions.

## Slide 26: Types of Cost Estimates
A rough order of magnitude (ROM)
  The time frame for this type of estimate is often three or more years prior to project completion.
  A ROM estimate’s accuracy is typically -50 percent to +100 percent, meaning the project’s actual costs could be 50 percent below the ROM estimate or 100 percent above.
  For example, the actual cost for a project with a ROM estimate of $100,000 could range from $50,000 to $200,000.

## Slide 27: Types of Cost Estimates
A budgetary estimate
  is used to allocate money into an organization’s budget.
  Many organizations develop budgets at least two years into the future.
  Budgetary estimates are made one to two years prior to project completion.
  The accuracy of budgetary estimates is typically 10 percent to 25 percent, meaning the actual costs could be 10 percent less or 25 percent more than the budgetary estimate.

## Slide 28: Types of Cost Estimates
A budgetary estimate
  For example, the actual cost for a project with a budgetary estimate of $100,000 could range from $90,000 to $125,000.

## Slide 29: Types of Cost Estimates
A definitive estimate
  provides an accurate estimate of project costs.
  Definitive estimates are used for making many purchasing decisions for which accurate estimates are required and for estimating final project costs.

## Slide 30: Types of Cost Estimates
A definitive estimate
  provides an accurate estimate of project costs.
  For example, if a project involves purchasing 1,000 personal computers from an outside supplier in the next three months, a definitive estimate would be required to aid in evaluating supplier proposals and allocating the funds to pay the chosen supplier.

## Slide 31: Types of Cost Estimates
A definitive estimate
  Definitive estimates are made one year or less prior to project completion. A definitive estimate should be the most accurate of the three types of estimates. The accuracy of this type of estimate is normally 5 percent to 10 percent, meaning the actual costs could be -5 percent less or +10 percent more than the definitive estimate. For example, the actual cost for a project with a definitive estimate of $100,000 could range from $95,000 to $110,000.

## Slide 32: Processes for project cost management
Controlling costs involves
  controlling changes to the project budget.
  The main outputs of the cost control process are
    work performance information, cost forecasts, change requests, and project management plan updates, and project documents updates.

## Slide 33: Controlling Costs
Purpose of Cost Control
Track project spending against the approved budget
Identify variances early and take corrective actions
Maintain financial health of the project
Ensure spending aligns with progress
Key Activities
Monitoring cost performance
Comparing planned vs. actual cost
Updating cost forecasts
Managing changes to cost baseline
Communicating status to stakeholders

## Slide 34: Controlling Cost
  Earned Value Management (EVM)
EVM is a powerful technique for measuring project performance using scope, schedule and cost data.
EVM Integrates Three Dimensions:
Scope – What work was planned? What is completed?
Schedule – When should the work be done?
Cost – How much should the work cost? How much did it cost?

## Slide 35: Earned Value Management (EVM)
1. Planned Value (PV)
Budgeted cost for work scheduled to be done, Also called BCWS
Example: “We planned to complete 40% of the work by today.”
2. Earned Value (EV)
Budgeted cost of work that has actually been completed, Also called BCWP
Example: If total budget = $100,000 and 25% of work is completed → EV = 25,000
3. Actual Cost (AC)
Actual cost spent for the work performed, Also called ACWP
Example: We spent $30,000 so far

## Slide 36: EVM Variance Calculations
Variance shows whether the project is ahead or behind.
1. Cost Variance (CV)
CV = EV – AC Positive → under budget / Negative → over budget
EV = 40,000 AC = 50,000
CV = –10,000 (over budget)
2. Schedule Variance (SV)
SV = EV – PV Positive → ahead of schedule / Negative → behind schedule
EV = 40,000 PV = 60,000
SV = –20,000 (behind schedule)

## Slide 37: EVM Performance Indexes
Indexes show efficiency.
1. Cost Performance Index (CPI)
CPI = EV / AC CPI > 1 → cost efficient | CPI < 1 → spending too much
Example: EV = 80,000 AC = 100,000
CPI = 0.80 → Project is only 80% efficient
2. Schedule Performance Index (SPI)
SPI = EV / PV SPI > 1 → ahead of schedule | SPI < 1 → behind schedule
Example: EV = 80,000PV = 100,000
SPI = 0.80 → Only 80% of planned work accomplished

## Slide 38
National University Of Modern Languages H-9 Islamabad
Thank you
National University Of Modern Languages H-9 Islamabad