Lecture-6 Project  Schedule Management

## What is Project Schedule Management?

Project Schedule Management is about planning, making, and controlling the project timeline so the project finishes on time.

- What work needs to be done?

- In what order?

- How long will it take?

- Are we on time or getting late?

## Six Main Processes of Project Schedule Management

## 1. Planning Schedule Management
This process decides how the project schedule will be planned, managed, and controlled during the whole project.

## 1.1 Project Schedule Model Development

Decides how the project schedule will be created.
It explains what method or tool will be used to make the schedule.

## 1.2 Level of Accuracy and Units of Measure

Defines how accurate time estimates should be and how time will be measured.

## 1.3 Control Thresholds

Defines how much delay is acceptable before taking action.

## 1.4 Rules of Performance Measurement

Defines how progress will be measured and tracked.

## 1.5 Reporting Formats

Defines how and when schedule reports will be shared.
It decides the format and frequency of schedule reports.

## 1.6 Process Description

Explains how all schedule management processes will be performed.

## 2. Defining Activities

What it means:
Identifying all tasks that must be done to complete the project.

## 3. Sequencing Activities

What it means:
Deciding the order in which activities should be done. It involve evaluating the reasons for dependencies. And there types.

### Types of Dependencies (Easy)

- Mandatory (Hard logic):
Must happen in order
Example: You must write code before testing it

- Discretionary (Soft logic):
Chosen by the team
Example: Finish design before coding (best practice)

- Internal dependencies:
Relationship between project activities that are controlled by project team
Example: Unit testing before system testing

- External dependencies:
Relationship between project and non project activities depend on outside factors
Example: Waiting for hardware delivery

Tool used:
👉 Network Diagrams (shows task relationships)

## 4. Estimating Activity Duration

What it means:
Estimating how much time each activity will take.

### PERT (Simple Explanation)

Used when time is uncertain.

PERT uses:

- Optimistic time (best case)

- Most likely time

- Pessimistic time (worst case)

PERT weight average = (optimistic time +4*(most likely time)+pessimistic time)/6

It gives a more realistic estimate.

## 5. Developing the Schedule

What it means:
Creating the final project timeline.

In simple words:
Put all tasks, order, and time together into one schedule.
Gantt Chart (bar chart showing tasks vs time)

## 6. Controlling the Schedule

What it means:
Monitoring the schedule and handling changes.

Includes:

- Tracking progress

- Finding reasons for delays

- Updating schedule if needed

Lecture 8- Project Cost Management

## 1. What is Project Cost Management?

Project Cost Management is about planning, estimating, budgeting, and controlling costs so that the project is completed within the approved budget.

### Why is it important?

- Many projects fail because they cost more than planned

- IT projects often have hidden costs

- Helps use money and resources efficiently

- Allows management to track financial performance

## 2. Main Processes of Project Cost Management

There are four main processes:

- Planning Cost Management

- Estimating Costs

- Determining the Budget

- Controlling Costs

## 1. Planning Cost Management

This process defines how costs will be managed throughout the project. It include planning, executing and controlling project cost.

### Output:

- Cost Management Plan

### What does it include?

#### a) Level of Accuracy

- How much rounding is allowed in estimates
Example: rounding costs to the nearest $100

#### b) Units of Measure

- Defines how costs are measured

  - Labor → hours or days

  - Hardware → dollars or number of units

- Avoids confusion between departments

#### c) Organizational Procedure Links

- This connects cost management processes to organizational system.

- Uses Work Breakdown Structure (WBS).

- Example: A control account code like CA-1001 for tracking expenses.

#### d) Control Thresholds

- Limits for acceptable cost variation

- Example:
Budget = $50,000
Threshold = 10%
If cost changes more than $5,000, action is required

#### e) Rules of Performance Measurement

- Defines how and when costs are tracked

- Example: Checking costs every two weeks

- Uses metrics like CPI (Cost Performance Index)

#### f) Reporting Formats

- Describe the format and frequency of cost reports required for the project.

- Example: Weekly cost reports with tables and graphs

#### g) Process Descriptions

- Explains how cost management processes are performed

- Example:

  - Collect vendor estimates

  - Approve budgets

  - Track weekly expenses

  - Handle budget changes

## 2. Estimating Costs

This process is about estimating how much money is needed to complete the project.

Project managers must estimate costs carefully to avoid budget problems.

## Types of Cost Estimates

There are three types:

### 1. Rough Order of Magnitude (ROM)

- Estimate of what a project will cost.

- Very early estimate (a guesstimate)

- Used for project selection decisions

- Time frame: 3+ years before completion

- Accuracy: –50% to +100%

Example:
ROM = $100,000
Actual cost may be between $50,000 and $200,000

### 2. Budgetary Estimate

- Used to allocate money into an organization’s budget.

- Time frame: 1–2 years before completion

- Accuracy: –10% to +25%

Example:
Budget = $100,000
Actual cost may be $90,000 to $125,000

### 3. Definitive Estimate

- Provide an accurate estimate of project costs.

- Used for purchasing and final decisions

- Time frame: less than 1 year before completion

- Accuracy: –5% to +10%

Example:
Estimate = $100,000
Actual cost may be $95,000 to $110,000

## 3. Determining the Budget

- This process aggregates all estimated costs to establish a total project budget.

- Deciding the final amount of money needed to complete the project.

Cost Baseline

Total project budget

## 4. Controlling Costs

This process ensures that the project does not exceed the budget.

### Purpose:

- Track spending

- Find cost problems early

- Take corrective actions

- Maintain project financial health

### Key Activities:

- Monitoring cost performance

- Compare planned vs actual costs

- Update cost forecasts

- Manage budget changes

- Inform stakeholders

## Earned Value Management (EVM)

EVM measures project performance using:

- Scope

- Schedule

- Cost

### Key Terms:

#### 1. Planned Value (PV)

- Budgeted cost of work planned

- Example: 40% work planned

#### 2. Earned Value (EV)

- Budgeted cost of completed work

- Example:

  - Total budget = $100,000

  - Work completed = 25%

  - EV = $25,000

#### 3. Actual Cost (AC)

- Actual money spent

- Example: $30,000 spent

## 9. EVM Variances

### Cost Variance (CV)

CV = EV – AC

- Positive → under budget

- Negative → over budget

Example:
EV = 40,000
AC = 50,000
CV = –10,000 → over budget

### Schedule Variance (SV)

SV = EV – PV

- Positive → ahead of schedule

- Negative → behind schedule

Example:
EV = 40,000
PV = 60,000
SV = –20,000 → behind schedule

## 10. EVM Performance Indexes

### Cost Performance Index (CPI)

CPI = EV / AC

- CPI > 1 → cost efficient

- CPI < 1 → over budget

Example: 
CPI = 0.80 → only 80% efficient

### Schedule Performance Index (SPI)

SPI = EV / PV

- SPI > 1 → ahead of schedule

- SPI < 1 → behind schedule

Example:
SPI = 0.80 → only 80% work completed

## 7. Basic Principles of Cost Management

### a) Profit Formula

Profit = Revenue – Expenditure

### b) Life Cycle Costing

- Looks at total cost over the entire life of the project

- Not just development, but maintenance and support too

### c) Direct Costs

- Directly related to project work
Examples:

  - Salaries

  - Equipment

  - Software licenses

### d) Indirect Costs

- Not directly linked but necessary
Examples:

  - Electricity

  - Paper

  - Office rent

### e) Sunk Cost

- Money already spent

- Cannot be recovered

- Should not affect future decisions

### f) Learning Curve Theory

- As more items are produced, cost per unit decreases

- Example:

  - First device is expensive

  - 1000th device is cheaper

### g) Reserves

Extra money kept for risks.

#### 1. Contingency Reserves (Known unknowns)

- For expected risks

- Example: Employee turnover

- Included in cost baseline

#### 2. Management Reserves (Unknown unknowns)

- For unexpected events

- Example:

  - Project manager gets sick

  - Supplier goes out of business

Project  Communication Management

## What is Project Communication Management?

Project Communication Management is about making sure the right information reaches the right people at the right time during a project.
It helps team members, managers, and stakeholders understand what is happening in the project and avoid confusion or delays.

## 1. Project Communication Management Processes

### 1.1 Planning Communication Management

This process decides how communication will happen in the project.

It answers:

- Who needs information?

- What information is needed?

- How will it be shared? (email, meeting, report)

- How often will it be shared?

📌 Example: Deciding to send weekly progress reports to the project manager.

### 1.2 Managing Communications

This process is about sharing information as planned.

It includes:

- Sending reports

- Holding meetings

- Sharing updates and documents

- Responding to emails and messages

📌 Example: Sending a weekly status report or conducting a team meeting.

### 1.3 Monitoring Communications

This process checks whether communication is effective or not.

It ensures:

- Messages are understood

- Stakeholders are satisfied

- Communication problems are fixed

📌 Example: Getting feedback from team members to see if reports are clear.

## 2. Methods for Communication

### 2.1 Formal Communication

Formal communication is official and documented.

Examples:

- Project reports

- Emails

- Contracts

- Official meetings

- Memos

📌 Used for important and professional information.

### 2.2 Informal Communication

Informal communication is casual and not officially recorded.

Examples:

- Quick chats

- Phone calls

- WhatsApp messages

- Friendly discussions

📌 Used for quick updates and teamwork.

## 3. Classification of Communication Methods

### 3.1 Interactive Communication

This is two-way communication where people talk and respond immediately.

Examples:

- Meetings

- Video calls

- Phone calls

- Face-to-face discussions

📌 Best for complex topics and quick decisions.

### 3.2 Push Communication

Information is sent to people without immediate feedback.

Examples:

- Emails

- Notices

- Reports

- SMS

📌 Sender pushes information, but does not know if it was understood.

### 3.3 Pull Communication

Information is stored and people access it when needed.

Examples:

- Project websites

- Shared folders

- Dashboards

- Knowledge bases

📌 Used when information is large or for many people.

Project  Quality  Management

## What is Project Quality Management?

Project Quality Management means making sure the final product meet the quality standards and customer needs.

In simple words:
👉 Do the right work
👉 Do it correctly
👉 Make the customer satisfied

Quality means:

- Meeting requirements

- Being fit for use

- Working as expected

## Purpose of Project Quality Management

The main purpose is to ensure the project delivers what the customer needs, without defects or major problems .

## Main Processes of Project Quality Management

### 1. Planning Quality Management

Identify the quality standards related to the project and how to satisfy them.

It includes:

- What quality standards to follow

- How quality will be achieved

- What rules and procedures will be used

👉 Plan first how quality will be maintained

### 2. Managing Quality

This process focuses on doing quality-related activities during the project.

It includes:

- Following the quality plan

- Performing tests and evaluations

- Creating quality reports

👉 Make sure work is done according to the quality plan

### 3. Controlling Quality

It involves monitoring specific project result to ensure that they are correct, complete and meet customer expectation.

It includes:

- Inspecting deliverables

- Finding defects

- Making sure customer expectations are met

👉 Check if the output is correct and acceptable

## Tools and Techniques for Quality Control

### Cause-and-Effect Diagram (Fishbone Diagram)

- Helps find the root cause of a problem

- Shows why a defect happened

### Checksheet

- Used to collect and analyze data

- Helps find patterns (e.g., most complaints on certain days)

## Cost of Quality

Cost of Quality means money spent to achieve good quality or fix poor quality.

### 1. Prevention Cost

- Cost to avoid mistakes

- Training, planning, quality studies

### 2. Appraisal Cost

- Cost to check quality

- Inspection and testing

### 3. Internal Failure Cost

- Cost of fixing errors before delivery

- Rework, redesign, scrap

### 4. External Failure Cost

- Cost of errors after delivery

- Warranty, complaints, loss of custome

### 5. Measurement & Test Equipment Cost

- Cost of tools and machines used for testing quality

Project  Resource Management

## Project Resource Management

Project Resource Management is about planning, getting, using, and controlling all the resources needed to complete a project successfully.

Resources include:

- Human resources: project manager, team members, sponsors, customers, suppliers, support staff

- Physical resources: equipment, tools, materials, facilities, and supplies

The main goal is to use resources efficiently so the project finishes on time, within budget, and with good quality.

## Processes of Project Resource Management

### 1. Planning Resource Management

This process decides how resources will be estimated, acquired, managed, and used during the project.
It is planning who will do what, what resources are needed, and how they will be managed.

### 2. Estimating Activity Resources

This process estimates how many people and physical resources are required to complete each task.

It answers: How many people, tools, or materials are needed for each activity?

### 3. Acquiring Resources

This process involves getting the required resources for the project.
It is about hiring people, assigning staff, and obtaining equipment or materials.

### 4. Developing the Project Team

This process focuses on improving team skills and teamwork to increase performance.
It helps the team work better together through training, motivation, and team-building activities.

### 5. Managing the Project Team

This process involves monitoring and guiding team members during the project.
It is about leading the team, solving problems, and keeping everyone productive.

### 6. Controlling Resources

This process ensures physical resources are used as planned and checks for overuse or shortage.

It checks whether resources are being used correctly and fixes problems if needed.

Project Risk Management

Project Risk Management is the process of identifying possible problems (risks), analyzing them, and taking actions effects so the project can be completed successfully.

Processes:

- Plan Risk Management
Decide how risks will be handled in the project.

Output :risk management plan

- Identify Risks
Find and list all possible risks that may affect the project.

Output: risk register, risk report, and project documents updates

- Qualitative Risk Analysis
involves prioritizing risks based on their probability of occurrence and impact.

Output: project documents updates

- Quantitative Risk Analysis
Use numbers or data to see how much risks can affect project objectives.

Output: project documents updates

- Plan Risk Responses
Decide what actions to take to avoid, reduce, or control risks.

Output: updates Project management plan and project documents

- Implement Risk Responses
Apply the planned actions to deal with risks.

Output: project documents updates and change requests

- Monitor Risks
Track risks continuously, identify new ones, and check if responses are working.

Output: work performance information, change requests, updates documentation.

Purpose:
To reduce uncertainty, avoid problems, and achieve project goals smoothly.